## CKAD Kubernetes YouTube Series
Task ID | Task Name | Owner | Start Date | End Date | Duration(Workdays) | Status | Priority | Notes
P1.1 | Exam Setup & Fast CLI Navigation | Lead | 2026-10-01 | 2026-10-02 | 2 | Not Started | P0 | Aliases dry-run setup
P1.2 | Pod Creation & Imperative Commands | Lead | 2026-10-05 | 2026-10-06 | 2 | Not Started | P0 | Imperative pod generation
P2.1 | Multi-Container Pod Patterns | Lead | 2026-10-07 | 2026-10-09 | 3 | Not Started | P0 | Sidecar Ambassador Adapter
P2.2 | Init Containers & Multi-Stage Builds | Lead | 2026-10-12 | 2026-10-13 | 2 | Not Started | P0 | Pre-req tasks & initialization
P2.3 | Jobs & CronJobs | Lead | 2026-10-14 | 2026-10-16 | 3 | Not Started | P0 | Parallelism backoff limits
P2.4 | Persistent & Ephemeral Volumes | Lead | 2026-10-19 | 2026-10-21 | 3 | Not Started | P0 | PV PVC emptyDir hostPath
P3.1 | ConfigMaps & Secrets | Lead | 2026-10-22 | 2026-10-23 | 2 | Not Started | P0 | Env vars volume mounts
P3.2 | SecurityContexts & ServiceAccounts | Lead | 2026-10-26 | 2026-10-28 | 3 | Not Started | P0 | runAsUser capabilities RBAC
P3.3 | Resource Quotas Limits & Requests | Lead | 2026-10-29 | 2026-10-30 | 2 | Not Started | P0 | CPU memory bounds LimitRanges
P3.4 | Authentication Authorization & Admission | Lead | 2026-11-02 | 2026-11-03 | 2 | Not Started | P0 | RBAC CRDs basic access
P4.1 | Services & Endpoints | Lead | 2026-11-04 | 2026-11-06 | 3 | Not Started | P1 | ClusterIP NodePort LoadBalancer
P4.2 | Ingress Rules & Routing | Lead | 2026-11-09 | 2026-11-10 | 2 | Not Started | P1 | Host path routing TLS
P4.3 | NetworkPolicies | Lead | 2026-11-11 | 2026-11-13 | 3 | Not Started | P1 | Ingress Egress pod selectors
P5.1 | Deployments Rolling Updates & Rollbacks | Lead | 2026-11-16 | 2026-11-17 | 2 | Not Started | P1 | rollout status undo revision
P5.2 | StatefulSets & DaemonSets | Lead | 2026-11-18 | 2026-11-20 | 3 | Not Started | P1 | Persistent identity node pods
P5.3 | Deployment Strategies & Helm | Lead | 2026-11-23 | 2026-11-24 | 2 | Not Started | P1 | Canary Blue Green Helm charts
P6.1 | Health Checks & Probes | Lead | 2026-11-25 | 2026-11-27 | 3 | Not Started | P2 | Liveness Readiness Startup
P6.2 | Container Logging & Troubleshooting | Lead | 2026-11-30 | 2026-12-01 | 2 | Not Started | P2 | kubectl logs debug containers
P6.3 | Monitoring & Metrics | Lead | 2026-12-02 | 2026-12-03 | 2 | Not Started | P2 | kubectl top API deprecations
Formulas:
Duration(Workdays) = NETWORKDAYS([Start Date],[End Date])